## Home
CS 527 Group 7 Project Status
Click on Buttons for easy navigation
Project Layout
Action Items
Navigation Planning

## ActionItemsChecklist
Category | Checklist Items | Status | Person Responsible | Remarks
I. Account functionality (10 points) | [] register customers | In Progress | Ziyu
| [] login (for all customers, admin, customer reps) | In Progress | Weihao
| [] logout (for all customers, admin, customer reps) | In Progress | Weihao
II. Browsing and search functionality (15 points) | [] search for train schedules by origin, destination, date of travel (5 points) | Done | Pranika
| [] browse the resulting schedules (5 points) | Done | Pranika
| [] see all the stops a train will make, fare etc. | Done | Pranika
| [] sort by different criteria (by arrival time, departure time, fare) (5 points) | In Progress | Pranika
III. Reservations (15 points) | [] a customer should be able to make a reservation for a specific route (round-trip/one way) (5 points) | In Progress | Kashish
| [] get a discount in case of child/senior/disabled (2 points) | Yet to Start | Kashish
| [] cancel existing reservation (3 points) | Yet to Start | Kashish
| [] view current and past reservations with their details (separately). (5 points) | Yet to Start | Kashish
IV. Admin functions (30 points) | [] Admin (create an admin account ahead of time) | Done
| [] add, edit and delete information for a customer representative (9 points) | In Progress | Pranika
| [] obtain sales reports per month (3 points) | Yet to Start
| [] produce a list of reservations: (5 points) | Yet to Start
| [] by transit line | Yet to Start
| [] by customer name | Yet to Start
| [] produce a listing of revenue per: (5 points) | Yet to Start
| [] transit line | Yet to Start
| [] customer name | Yet to Start
| [] best customer (4 points) | Yet to Start
| [] best 5 most active transit lines (4 points) | Yet to Start
VI. Customer representative: (30 points) | [] edit and delete information for train schedules (6 points) | In Progress | Weihao
| [] customers browse questions and answers (4 points) | Yet to Start
| [] customers search questions by keywords (4 points) | Yet to Start
| [] customers send a question to the customer service (3 points) | Yet to Start
| [] reps reply to customer questions (3 points) | Yet to Start
| [] produce a list of train schedules for a given station (as origin/destination) (5 points) | Yet to Start
| [] produce a list of all customers who have reservations on a given transit line and date. (5 points) | Yet to Start

## Project Layout
Rubric | Functionality | JSP | Remarks
I Account Information | Register Customers | register.jsp
| Login | login.jsp
| Logout | logout.jsp
II Browsing and Search Functionality | Search | search.jsp | Drop downs for origin, destination, date of travel and submit button to show results
| Browse |  | Browse the resulting schedules - this will show the details of each schedule This needs to have a sort functionality

## NavigationPlanning
Navigation
Nav bar
| Home | Search | Reserve | My Booking | Login/Register
| Create | Edit | Reports | Admin view | Admin
| Register page functionality | Retrieve the records and each record has an edit button | Sales Report
|  | Functionality from Register Page | Reservations Report
Revenue Listing
customer
Note on N5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It does nothing when not logged in, when clicked, it takes user to login screen. If the user is logged in, it shows the bookings/reservations

## Action Items (hidden)
Person Responsible | Action Items
Kashish | Sending SQL for the database (concerned tables for now) with data
Pranika | search
Weihao | login logout
Ziyu | register (sign up)
Person Responsible | Action Items
Kashish | Home, Reservation
Pranika | add, edit and delete information for a customer representative
Weihao | edit and delete information for train schedules
Ziyu | register (sign up)
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Session Attributes
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: By default role will be customer Reply: Continue
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: By default role will be customer Reply: Continue

## Status (hidden)
In Progress | Kashish
Done | Pranika
Yet to Start | Weihao
Review Required | Ziyu